## Slide 1: 项目管理实践 制定项目计划
苑旭
Program Manager
Onest Network Technology Inc.

## Slide 2: 计划阶段子里程碑
选定技术架构
需求确认书被认可(概念设计)
系统设计基准完成(逻辑和物理设计)
开发和测试环境搭建完成
项目计划(规划)被认可

## Slide 3: 项目计划内容
目的：规划和确定项目管理范围
交付成果
  项目规划文档
  项目总体时间表(Schedule)
产品范围
项目范围
范围

## Slide 4: 计划是一个团队活动
计划 | 驱动角色
沟通计划 | 产品管理
开发计划 | 开发
培训计划 | 用户体验
安全计划 | 开发/发布管理
测试计划 | 测试
预算计划 | 程序管理
部署计划 | 发布管理
采购计划 | 发布管理/程序管理
试用计划 | 发布管里

## Slide 5: 创建项目规划
沟通计划
部署计划
采购计划
开发计划
预算计划
容量计划
培训计划
试用计划
测试计划
安全计划
项目规划
(项目主计划)

## Slide 6: 部署计划
主要内容 | 方法
安装策略 | 分阶段还是一次部署，一个站点一个站点，还是一个部门一个部门，是推还是拉的方式
部署意外的策略 | 并行系统，完全备份，还是没有意外策略
部署机制 | 全自动安装，脚本安装，还是纯手工
部署资源 | 内部ITG，外部联系人
系统支持策略 | 分层的技术支持，使用支持

## Slide 7: 试用计划
只要内容 | 方法
选择试用用户 | 最紧急的业务需求，直接或受影响的用户，失败的风险
使用范围 | 部分功能的部署试用，还是整个方案的试用
参与者数量 | 一小部分，一个部门，还是全体用户
反馈机制 | 整体，还是逐个站点/位置

## Slide 8: 采购计划
Hardware and Software Acquisition Considerations | Physical Facilities Considerations
Vendor contracts Order processing Preconfiguration Warehousing/staging Receiving/storage Obsolete equipment disposal | Building permits End-user workspace Cabling Power / air conditioning Server room

## Slide 9: 测试计划
主要内容 | 方法
主要执行的测试类型以及每种测试类型所用的技术/功能 | 单元测试，整合测试，性能测试，压力测试，可用性测试，容量测试..
测试版本和成功条件 | 全文档化的测试场景和测试结果
变更控制 | Check-in/out 过程和信息传递过程
配置管理 | 集中管理软硬件和文档的规范以及本地配置规范
问题跟踪管理 | 问题识别、优先级、bug数据库

## Slide 10: 培训计划
主要内容 | 方法
培训听众 | 所有受影响用户，IT管理员，支持组成员
培训方式 | 动手实验，基于电脑还是web培训，一对一还是演讲形式
培训素材开发 | 购买还是自己构建
培训期限 | 全天，半天，还是几个小时
培训交付时间 | 部署之前，还是构建之后，或者是根据用户需要时培训
培训资源 | 外/外部讲师

## Slide 11: 沟通计划
Potential Audiences | Potential Vehicles | Potential Messages
All users | Face-to-face meetings | What’s happening and why
All affected users | Memos | When it will happen
Management | Newsletters | Who it will affect
All IT personnel | Intranet | How users will be affected
IT administrators | E-mail | How users should prepare
Help desk | Voice mail | How users can get more information

## Slide 12: Capacity Plan
The capacity plan addresses:
How much additional traffic the solution will generate
How the additional traffic will affect users
Whether current systems and networks are capable of handling the expected usage
What hardware/services may be required to increase system and network capacity
What additional requirements are needed for client machines

## Slide 13: Security Plan
The security plan describes:
How established security guidelines will be implemented
What actions will be taken to mitigate any risk in the absence of established security guidelines
What interim security measures will be taken if established security measures conflict with the successful completion of the project

## Slide 14: Budget Plan
Identify expected costs and cost constraints from the following sources:
Functional specification
Other project plans (for example, development, deployment, pilot, purchasing and facilities, test, training, communications, capacity, and security)
Customer expectations

## Slide 15: Preparing Estimates from Plans
Identify required work based on plans and specifications
Create a work breakdown structure (WBS)
  Divide work into individual tasks and level of effort
  Break down tasks and subtasks by role
  Create task durations greater than four hours, but less than one week
Estimates –The data used to create budgets and schedules

## Slide 16: Techniques for Estimating
Use bottom-up estimating to determine task durations
Use prototyping to aid in estimation
Allocate buffer time as a discrete task

## Slide 17: Integrating and Synchronizing the Plans
Integration ensures correlation of tasks and deliverables among the individual plans
Synchronization ensures the proper sequencing of activities
Program management role drives integration and synchronization to compile and baseline the master project plan
Interim milestone – Master project plan baselined

## Slide 18: Lesson Review
What is the relationship between approaches and plans?
Identify the type of plan typically associated with each MSF team role.
How does planning lead to the preparation of estimates?
Why are the techniques of bottom-up estimating and allocating buffer time effective?
What are two outcomes of plans that are integrated and synchronized correctly?